## Sheet1
High Priority Task For Right Freelancer
Changes | Date | Done or Padding | Worker Name
Admin
https://www.rightfreelancer.com/admin miranweb@gmail.com
install all plugins and check | 2024-02-10 | done | nayeem
Import Countrys and Regions and City
Routing Changes
https://www.rightfreelancer.com/packages/all https://www.rightfreelancer.com/packages https://www.rightfreelancer.com/blogs/all https://www.rightfreelancer.com/blog
Profile Compilation > remove 2 Factor Authentication > client and freelancer end this is will be optional | 2024-03-10 | done | nayeem
Client End ---------- 1. Signup and login + email template check 2. Profile Compilation Profile Settings Identity Verification 3. Post a Job interview and messages give job |  | done
Please login as a freelancer account > Profile Details > user showing Active change to online |  | done
Job list page client Verified just after email showing need discuss
Talents Rated Plus backgourd image is missing in all pages like home page talents pages and profiles |  | done
inner page need meta titile and des |  | done
old user import on new project |  | done
Need to check notiification on contact us page, email delivery issue |  | Pending By Client Side
Chat should be real time
Need to check all the email templates and flows. |  | done
Stripe Prod Keys need to replace with test accounts. |  | done
Rename old jobs title and description. |  | Pending By Client Side
import Countries + State + Cities
Plugins need to add
Package plan need to control from admin panel
Project post and final test with payment to freelancer
Job post and final test with payment to freelancer
NameCheap Domain config
Cron job when add new project OR Job
Packages control from admin panel
Identity Verification NIC Passport and D |  | done
Package Logo size should be large in size
Sponser Company Home page section remove |  | Pending By Client
When new update push to server why images are removing , Urgent FIX
check all pages title text, not same like packages |  | done
Change Text and Title Buy Subscription to Packages web panel |  | done
ad management link not working user and client side
Top Freelancer of month Ratings Show on home page under the menu |  | done
Any category add admin panel but cannot show in web panel |  | done
user register email freelancer and client same email switch
user register 10 doller in wellet